## Sheet1
S.NO | Description | Responsibility center | Status | Remarks
1 | Track progress on the 6 service pillars | Safaricom & SHA | Ongoing | In Progress
2 | Resolve biometrics data issue with former vendor (MIBM) | SHA ICT Directorate | 2025-03-01 | Pending
3 | Develop a decryption mechanism for biometrics data | SHA ICT | 2025-03-01 | Pending
4 | Close WhatsApp groups to ensure data privacy compliance | Safaricom & SHA | 2025-01-25 | Planned
5 | Set up robust feedback and escalation mechanisms | Safaricom & SHA | 2025-02-25 | Planned
6 | Engage Airtel and Telkom for payment integration | SHA Team( Financial Services ) | 2025-02-25 | In Progress
7 | Address employer portal challenges (eligibility & reconciliation) | SHA ( beneficiary Management ) | 2025-01-25 | In Progress
8 | Provide training and user manuals for system navigation | SHA & konvertence Solutions | 2025-12-24 | Planned
9 | Accelerate the development of Accounts Receivable in ERP | SHA Finance & ICT Directorate | 2024-12-01 | Urgent
10 | Finalize patient encounter pre-authorization issues | SHA Claims Department | 2025-01-25 | In Progress
11 | Deploy additional RCOs to respond to queries ( enhance capacity0 | SHA Beneficiary Management | 2025-12-24 | Planned
12 | Strengthen customer support with Level 2 call center | Safaricom CX & SHA CX | 2025-02-01 | In Progress
13 | Develop brochures and manuals for RCOs | SHA (Beneficiary Management ) | 2025-01-01 | Planned
14 | Integrate Safaricom call center with SHA CX | Safaricom & SHA CX | 2025-02-01 | Planned
15 | Submit phased ERP development priorities | Safaricom Consortium | 2025-01-25 | Pending
16 | Prepare a board paper on registration of Refugees ,Aliens& Expatriates | SHA (Beneficiary Management) | 2025-02-25 | Planned
17 | Prepare reports of the key performance Metrics (Registration, Claims, case management ( Quarter 1 reports ) | SHA (Beneficiary Management) | 2024-12-01 | Pending
18 | Enhance system controls to mitigate against fraud, wastage and abuse | SHA (Claims Management) & Safaricom | 2025-01-01 | Pending